## STLC_Overview
SOFTWARE TESTING LIFE CYCLE (STLC) — Task Manager v2.0
Phase | Objective | Entry Criteria | Exit Criteria | Activities | Owner | Duration | Status
1. Requirement Analysis | Understand what needs to be tested | BRD/SRS documents available; Stakeholders accessible | All requirements reviewed & test basis signed off | Review requirements Identify testable features Clarify ambiguities Prioritize test areas | BA + QA Lead | 2 days | Completed
2. Test Planning | Define scope, approach, resources & schedule | Requirements analysis complete; Resources allocated | Test plan document approved by stakeholders | Define test scope (in/out) Select test types Choose tools (Postman, k6) Estimate effort Identify risks | QA Lead | 1 day | Completed
3. Test Case Design | Create detailed test cases & RTM | Test plan approved; Requirements finalized | All test cases written, reviewed & added to RTM | Write test cases (TC-001–TC-015) Create RTM Peer review Get sign-off | QA Engineers | 3 days | Completed
4. Test Environment Setup | Prepare backend, frontend & test data | Test cases ready; Infrastructure available | Environment verified & smoke-tested | Install Python 3.11 + FastAPI Setup React+Vite frontend Seed demo data Verify CORS & auth Run smoke tests | DevOps + Dev | 1 day | Completed
5. Test Execution | Execute all test cases & log defects | Environment ready; Test cases approved | All TCs executed; All Critical/High defects fixed | Execute TC-001–TC-015 Log defects (DEF-001–DEF-003) Retest fixes Update RTM Pass/Fail Regression testing | QA Engineers | 3 days | In Progress
6. Test Closure | Evaluate completion & document metrics | All planned tests executed; No P1 open defects | Test closure report signed off; Metrics archived | Compute pass rate Write closure report Lesson-learned meeting Archive RTM & STLC Sign-off for release | QA Lead | 1 day | Pending

## Test_Plan
TEST PLAN — Task Manager v2.0
1. PROJECT INFO
Project | Task Manager v2.0 — Full-stack CRUD App
Version | 2.0.0
Prepared By | QA Team
Date | 2025-06-01
Tools | Postman (API), k6 (Load), GitHub Actions (CI), pytest (Unit)
2. SCOPE — IN
Auth Module | Login / logout, token validation, 401 on bad creds
Task CRUD | Create, Read, Update, Delete via REST API
UI Interactions | Create/Edit modal, Delete confirm, search, filters
Stats Dashboard | Summary counts by status; live update on changes
Performance | Stats endpoint P95 < 200ms under 50 VUs
3. SCOPE — OUT
Email notifications | Not in v2.0 scope
Multi-user roles | Only admin user in current build
Persistent DB | In-memory store; no PostgreSQL in this version
4. TEST TYPES
Type | Description | Linked TCs
Functional | Verify all CRUD operations and auth flow | TC-001–TC-014
Negative | Invalid inputs, bad IDs, wrong credentials | TC-002, TC-004, TC-009
UI/UX | Confirm dialogs, error banners, filter pills | TC-010, TC-011, TC-013
Integration | Frontend ↔ Backend stats update flow | TC-014
Performance | k6 load test — 50 VUs for 30s | TC-015
5. RISKS & MITIGATIONS
Risk | Severity | Mitigation
CORS errors on Windows | High | Test with 127.0.0.1 instead of localhost
Route order bug in FastAPI | Critical | Stats route defined before /{task_id}
Missing Node.js | Medium | Document Node 18+ prerequisite in README
In-memory data loss on restart | Low | Document limitation; seed data auto-loads

## Test_Execution_Log
TEST EXECUTION LOG — Task Manager v2.0
TC-ID | Title | Module | Priority | Tester | Exec Date | Build | Status | Defect ID | Notes
TC-001 | Valid admin login | Auth | Critical | Alice | 2025-06-01 | v2.0.0 | Pass | — | Token returned correctly
TC-002 | Invalid login rejected | Auth | Critical | Alice | 2025-06-01 | v2.0.0 | Pass | — | 401 returned as expected
TC-003 | Create task via POST | Task Management | High | Bob | 2025-06-01 | v2.0.0 | Pass | — | 201 + ID in response
TC-004 | Create task missing title | Task Management | High | Bob | 2025-06-01 | v2.0.0 | Pass | — | 422 validation error shown
TC-005 | List all tasks | Task Management | High | Carol | 2025-06-01 | v2.0.0 | Pass | — | All 8 seed tasks returned
TC-006 | Filter by status=Open | Task Management | Medium | Carol | 2025-06-01 | v2.0.0 | Pass | — | Only Open tasks returned
TC-007 | Filter by priority=Critical | Task Management | Medium | Alice | 2025-06-01 | v2.0.0 | Pass | — | Correct subset returned
TC-008 | Update task status | Task Management | High | Bob | 2025-06-02 | v2.0.0 | Pass | — | Status updated to Closed
TC-009 | Update non-existent task | Task Management | Medium | Bob | 2025-06-02 | v2.0.0 | Pass | — | 404 with meaningful message
TC-010 | Delete with confirmation | UI | Critical | Alice | 2025-06-02 | v2.0.0 | Pass | DEF-001 | Confirm dialog now shown. DEF-001 fixed.
TC-011 | Cancel delete unchanged | UI | High | Alice | 2025-06-02 | v2.0.0 | Pass | — | Task preserved on cancel
TC-012 | Stats summary endpoint | Dashboard | High | Carol | 2025-06-02 | v2.0.0 | Pass | DEF-003 | Route order fixed. DEF-003 resolved.
TC-013 | Search by keyword | UI | Medium | Bob | 2025-06-02 | v2.0.0 | Pass | — | Filter works on title + description
TC-014 | Stats update after add | Dashboard | High | Carol | 2025-06-03 | v2.0.0 | In Progress | — | Frontend re-fetches on create
TC-015 | Performance load test | Performance | Low | Alice | 2025-06-03 | v2.0.0 | Pending | — | k6 test scheduled
EXECUTION SUMMARY |  |  |  | Pass Rate: |  | Passed: |  | Pending: